## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Owner | Progress (%)
GP-001 | Milestone Planning Workshop | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith | 75%
GP-002 | Market Opportunity Analysis | 2023-10-06 | 2023-10-15 | Not Started | Mike Johnson | 0%
GP-003 | Product Roadmap Development | 2023-10-16 | 2023-11-10 | In Progress | Sarah Lee | 50%
GP-004 | Resource Allocation & Budgeting | 2023-11-11 | 2023-11-25 | Not Started | David Brown | 0%
GP-005 | Risk Assessment & Mitigation Plan | 2023-11-26 | 2023-12-10 | Not Started | Lisa Wong | 0%
GP-006 | Growth Strategy Finalization | 2023-12-11 | 2023-12-20 | Not Started | Jane Smith | 0%