## Worksheet
Growth Planning - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Growth Planning
Project ID | Project Name | Status | Start Date | End Date | Budget ($)
PJ001 | Market Expansion Initiative | In Progress | 2024-01-15 | 2024-12-31 | 750,000
PJ002 | New Product Launch (Phase 1) | Planning | 2024-03-15 | 2024-11-30 | 587,500
PJ003 | Customer Retention Program | In Progress | 2024-02-15 | 2024-12-31 | 495,000
PJ004 | Digital Marketing Overhaul | Planning | 2024-01-31 | 2024-11-30 | 685,750
PJ005 | Talent Acquisition & Training | In Progress | 2024-01-31 | 2024-12-31 | 568,950
Page 1 of 5 ¦ Generated on:
Growth Planning - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Growth Planning
Task ID | Task Name | Assigned To | Status | Priority | Due Date
T001 | Market Research Analysis | Sarah Chen (Marketing) | Completed | High | 2024-01-31
T002 | Competitor Benchmarking Report | Liam Rodriguez (Strategy) | In Progress | High | 2024-03-15
T003 | New Product Feature Specification DraftAisha Patel (Product) | Not Started | High | 2024-03-15
T004 | User Experience Wireframes - Phase 1Daniel Kim (Design) | In Progress | Medium | 2024-03-31
T005 | Initial Prototype DevelopmentJessica Wong (Engineering) | Not Started | High | 2024-04-15
T006 | MVP Testing & Feedback CollectionElena Torres (QA) | Not Started | Medium | 2024-07-31
T007 | Campaign Creative Design - Q2 2024Fredrick Brown (Marketing) | Planning | Medium | 2024-03-31
T008 | Training Curriculum DevelopmentMaria Lopez (HR) | In Progress | High | 2024-04-15
Page 2 of 5 ¦ Generated on:
Growth Planning - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Growth Planning
Milestone ID | Milestone Name | Project | Target Date | Status
M001 | Market Research Finalized & Approved | Market Expansion Initiative | 2024-01-31 | Completed
M002 | New Product Concept ApprovalNew Product Launch (Phase 1) | 2024-03-15 | In Progress
M003 | Design Phase Complete - Wireframes & Prototypes ApprovedNew Product Launch (Phase 1) | 2024-05-15 | Not Started
M004 | MVP Development Completed & Internal Testing DoneNew Product Launch (Phase 1) | 2024-07-31 | Not Started
M005 | Q2 Marketing Campaign Launched & Initial Metrics CollectedDigital Marketing Overhaul | 2024-06-30 | Planning
M006 | Talent Onboarding Program Rollout - First Cohort CompleteTalent Acquisition & Training | 2024-05-15 | In Progress
M007 | Customer Retention Program Pilot Phase Complete & Analysis FinalizedCustomer Retention Program | 2024-11-30 | In Progress
M008 | Roadmap Presentation to Executive Team - Q2 2024 Review MeetingGeneral Growth Planning | 2024-05-31 | Not Started
Page 3 of 5 ¦ Generated on:
Growth Planning - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Growth Planning
Resource ID | Name | Role | Project Assignment(s) | % Allocation
R001 | Sarah ChenMarketing Manager | Market Expansion Initiative, Digital Marketing Overhaul (Part-Time) | 85%
R002 | Liam RodriguezStrategy Lead | New Product Launch (Phase 1), Growth Planning Oversight (Part-Time) | 75%
R003 | Aisha PatelProduct Manager | New Product Launch (Phase 1) | 100%
R004 | Daniel KimSenior UX Designer | New Product Launch (Phase 1), Digital Marketing Overhaul (Part-Time) | 65%
R005 | Jessica WongLead Engineer | New Product Launch (Phase 1) | 90%
R006 | Elena TorresQA Lead | New Product Launch (Phase 1) | 55%
R007 | Fredrick BrownMarketing Specialist - Campaigns | Digital Marketing Overhaul, Customer Retention Program (Part-Time) | 70%
R008 | Maria LopezHR Development Manager | Talent Acquisition & Training, Growth Planning (Part-Time) | 60%
Page 4 of 5 ¦ Generated on:
Growth Planning - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Growth Planning
Project | Budget ($) | Spent to Date ($) | Remaining Budget ($) | Status
Market Expansion Initiative | 750,000 | 213,547 | 536,453 | In Progress (28.5%)
New Product Launch (Phase 1) | 587,500 | 98,201 | 489,299 | In Progress (16.7%)
Customer Retention Program | 495,000 | 135,673 | 359,327 | In Progress (27.4%)
Digital Marketing Overhaul | 685,750 | 89,412 | 600,338 | In Progress (13.0%)
Talent Acquisition & Training | 568,950 | 77,125 | 491,825 | In Progress (13.6%)