## Growth Planning - Project Plan
Growth Planning - Project Plan (One Page)
Phase | Task | Owner | Start Date | End Date | Status | Budget ($)
Phase 1: Strategy Development
1 | Conduct Market Analysis | Jane Smith | 2023-10-01 | 2023-10-15 | In Progress | 5,000
1.1 | Define Target Audience Segments | Jane Smith | 2023-10-16 | 2023-10-25 | Pending | 3,500
Phase 2: Planning & Resource Allocation
2 | Develop Growth Strategy Framework | Mike Johnson | 2023-10-26 | 2023-11-15 | Pending | 8,000
2.1 | Allocate Budget & Resources | Mike Johnson | 2023-11-16 | 2023-11-30 | Pending | 6,500
Phase 3: Implementation
3 | Launch Digital Marketing Campaigns | Sarah Lee | 2023-12-01 | 2024-01-31 | Pending | 50,000
3.1 | Develop & Launch New Product Features | Daniel Brown | 2024-01-15 | 2024-03-31 | Pending | 75,000
Phase 4: Monitoring & Optimization
4 | Track KPIs & Performance Metrics | Emma Wilson | 2023-12-01 | 2024-06-30 | Pending | 15,000
Total: |  |  |  |  | 163,000