## Worksheet
Growth Planning - Project Plan (Planning View)
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete(Progress) | Milestones/Dependencies
GP-001 | Market Research & Analysis | Marketing Team | 2024-04-01 | 2024-05-15 | In Progress | 65% | None
GP-002 | Define Target Audience Segments | Product Strategy | 2024-05-16 | 2024-06-15 | To Do | 0% | Depends on GP-001
GP-003 | Develop Growth Strategy Framework | Business Development | 2024-06-16 | 2024-07-31 | To Do | 0% | Depends on GP-002
GP-004 | Validate Growth Assumptions with Pilot Group | R&D Team | 2024-08-01 | 2024-09-15 | To Do | 0% | Depends on GP-003
GP-005 | Finalize Growth Roadmap & Budget Approval | CFO Office | 2024-09-16 | 2024-10-31 | To Do | 0% | Depends on GP-004
GP-006 | Launch Growth Initiatives (Phase 1) | All Teams | 2024-11-01 | 2025-03-31 | To Do | 0% | Depends on GP-005