## Worksheet
Phase | Activity/Task | Owner | Start Date | End Date | Status | Budget (USD)
Initiation | Define Growth Objectives | Product Team Lead | 2023-10-01 | 2023-10-07 | In Progress | $5,000
Initiation | Stakeholder Alignment Workshop | Project Manager | 2023-10-08 | 2023-10-10 | Pending | $3,500
Planning | Market Research & Analysis | Market Analyst | 2023-10-11 | 2023-10-25 | Not Started | $8,000
Planning | Resource Allocation Plan Development | Operations Manager | 2023-10-15 | 2023-10-28 | In Progress | $6,500
Execution | Launch Pilot Program (Q4) | Marketing Manager | 2023-10-29 | 2023-11-30 | Pending | $15,000
Execution | Customer Onboarding Campaign | Customer Success Lead | 2023-11-01 | 2023-12-15 | Pending | $9,800
Monitoring & Evaluation | KPI Tracking Dashboard Setup | Data Analyst | 2023-11-15 | 2023-11-30 | Pending | $4,200
Monitoring & Evaluation | Mid-Cycle Review Report (Q4) | Project Manager | 2023-12-16 | 2023-12-31 | Pending | $7,500
Total Project Budget: | [5 empty] | $69,500