## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
T101 | Market Research & Analysis | Marketing Manager | 2024-04-01 | 2024-04-15 | In Progress | 65%
T102 | Product Development Phase 1 | Product Lead | 2024-04-10 | 2024-05-15 | Not Started | 0%
T103 | Cash Flow Forecasting (Q2) | Finance Manager | 2024-04-05 | 2024-04-30 | Completed | 100%
T104 | Website Redesign & SEO Optimization | Web Developer | 2024-04-20 | 2024-06-15 | In Progress | 45%
T105 | Customer Feedback Collection | Customer Success Lead | 2024-05-01 | 2024-05-31 | Not Started | 0%
T106 | Hire New Sales Representative | HR Manager | 2024-05-15 | 2024-06-30 | In Progress | 30%
T107 | Launch Marketing Campaign (Q2) | Marketing Manager | 2024-06-01 | 2024-06-30 | Not Started | 0%
Note:This is a sample project plan for growth planning in a small business. Update task statuses and dates as progress is made.