## Worksheet
Growth Planning - Project Plan Template
Purpose:Growth Planning ¦Template Type:Project Plan ¦Style/Version:Template Version
ID | Task Name | Description | Start Date | End Date | Responsible Person | Status | Budget (USD)
1 | Market Research Phase | Conduct comprehensive analysis of target markets and customer segments. | 2025-04-01 | 2025-04-15 | Jane Smith | In Progress | $8,500.00
2 | Product Development Sprint 1 | Design and prototype core product features based on research findings. | 2025-04-16 | 2025-05-14 | Mark Johnson | To Do | $35,000.00
3 | User Testing & Feedback Collection | Conduct usability tests with target users and gather feedback. | 2025-05-15 | 2025-06-14 | Lisa Chen | Not Started | $12,750.00
4 | Launch Campaign Planning | Develop marketing strategy and campaign calendar for product launch. | 2025-06-15 | 2025-07-31 | Daniel Rodriguez | Not Started | $24,300.00
5 | Final Product Release & Go-Live | Deploy product to production environment and official launch. | 2025-08-01 | 2025-08-15 | Sarah Williams | Not Started | $6,450.00
Total Estimated Budget: | [6 empty] | $87,000.00