## Worksheet
Growth Planning - Project Plan - Tracking View
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%)
T001 | Market Research & Analysis | Jane Doe | 2024-04-01 | 2024-04-15 | High Risk | 65%
T002 | Product Development Phase 1 | John Smith | 2024-04-16 | 2024-05-31 | In Progress | 75%
T003 | Design & Prototype Testing | Amy Johnson | 2024-05-15 | 2024-06-15 | In Progress | 45%
T004 | Marketing Strategy Development | Lisa Brown | 2024-06-16 | 2024-07-31 | Low Risk | 25%
T005 | User Feedback Collection | Mike Wilson | 2024-08-15 | 2024-09-30 | Low Risk | 5%
T006 | Final Product Launch Preparation | Sarah Lee | 2024-10-15 | 2024-11-30 | Low Risk | 0%
Overall Project Progress: |  |  |  |  | 48%
Last updated:April 5, 2024¦ Status reflects tracking view for Growth Planning