## Worksheet
Week | Goals & Objectives |  |  |  | Key Activities |  |  | Owner | Status
| Focus Area | Target Metric | Progress (%) | Milestones | Description | Deadline | Resources Needed
Week 1 | Market Research | User Acquisition Rate | 0% | Complete initial survey & competitor analysis | Conduct online surveys and benchmark competitors. | 2025-04-07 | Survey tool, analyst support | Alex Turner | Not Started
| Product Enhancement | Feature Adoption Rate | 0% | Define top 3 priority features | Review user feedback and prioritize enhancements. | 2025-04-07 | User insights, product manager
| Team Alignment | Cross-functional Collaboration Score | 0% | Kickoff meeting and roadmap sharing | Hold weekly planning session with all teams. | 2025-04-06 | Meeting room, presentation deck
Week 2 | Marketing Campaign Prep | Email Open Rate | 0% | Draft campaign content and design templates | Create email copy, visuals, and landing page mockups. | 2025-04-14 | Design team, copywriter | Jenna Lee | Not Started
| Onboarding Optimization | Time-to-First-Value (TTV) | 0% | Redesign onboarding flow prototype | Develop new onboarding journey with feedback loops. | 2025-04-14 | User testing kit, UX designer
| Data Infrastructure | Data Pipeline Uptime | 0% | Assess current data pipeline stability | Run diagnostics and document system performance. | 2025-04-13 | Data engineer, monitoring tools
Week 3 | Launch Pilot Campaign | Conversion Rate (Pilot) | 0% | Deploy campaign to 10% user segment | A/B test messaging and targeting options. | 2025-04-21 | Marketing automation tool, analytics team | Marcus Chen | Not Started
| Feature Development (Sprint 1) | Development Velocity | 0% | Complete MVP of feature A | Frontend & backend implementation, peer review. | 2025-04-21 | Developer team, CI/CD pipeline
| User Feedback Loop | Feedback Response Time | 0% | Set up feedback collection system | Integrate in-app feedback widget and review process. | 2025-04-20 | Product team, support staff
Week 4 | Analyze Pilot Results | Pilot ROI Metrics | 0% | Review campaign performance & optimize strategy | Analyze KPIs and prepare optimization report. | 2025-04-28 | Data analyst, marketing lead | Sophia Patel | Not Started
| Feature QA & Testing | Defect Density (Per 1k lines) | 0% | Complete testing for feature A | Run regression, usability, and security tests. | 2025-04-28 | QA team, test environment
| Weekly Review & Planning | Action Items Completion Rate | 0% | Review weekly progress and plan next week | Team retrospective and roadmap refinement. | 2025-04-29 | All team members, facilitator
Last updated: April 5, 2025 ¦ Project Plan Version: Weekly - Growth Planning