## Worksheet
Growth Planning Project Template
Phase | Task Description | Owner | Start Date | End Date | Status | Budget (USD)
Initiation | Define project scope and objectives | Project Manager | 2024-01-05 | 2024-01-15 | In Progress | $8,500.00
Research & Analysis | Market research and competitor analysis | Marketing Analyst | 2024-01-16 | 2024-01-31 | To Do | $6,750.00
Strategy Development | Create growth strategy and KPIs framework | Strategy Lead | 2024-02-01 | 2024-02-15 | To Do | $15,300.00
Implementation Plan | Develop detailed execution roadmap and timeline | Operations Manager | 2024-02-16 | 2024-03-15 | To Do | $18,900.00
Resource Allocation | Assign team members and secure tools/resources | HR & IT Coordinator | 2024-03-16 | 2024-03-31 | To Do | $5,650.00
Pilot Launch | Execute initial 2-week pilot program in target market | Product Manager | 2024-04-01 | 2024-04-15 | To Do | $7,895.00
Evaluation & Optimization | Review pilot results and refine strategy for scaling | Data Scientist | 2024-04-16 | 2024-05-31 | To Do | $13,500.00
Full Scale Rollout | Launch full project across all targeted regions/markets | Project Director | 2024-06-01 | 2024-11-30 | To Do | $85,750.00
Total | [6 empty] | $162,245.00