## Worksheet
Growth Planning - Project Template
Phase | Objective | Key Activities | Responsible Team | Start Date | End Date | Status
Initiation | Define project scope and goals for growth strategy. | - Conduct market analysis - Identify target customer segments - Define KPIs for success | Strategy Team | 2025-01-15 | 2025-01-31 | In Progress
Planning | Develop actionable roadmap and resource allocation. | - Draft growth plan - Allocate budget and personnel - Set milestones & deadlines | Project Management Office | 2025-02-01 | 2025-02-14 | To Do
Execution | Implement growth initiatives across departments. | - Launch marketing campaigns - Optimize sales funnel - Roll out new product features | Marketing, Sales, Product Teams | 2025-02-15 | 2025-04-30 | To Do
Monitoring & Evaluation | Track performance and adjust strategy as needed. | - Monthly progress reviews - Analyze KPIs and metrics - Report findings to stakeholders | Analytics Team, Leadership | 2025-03-01 | 2025-06-30 | To Do
Review & Closeout | Assess outcomes and document lessons learned. | - Final performance report - Conduct retrospective meeting - Archive project documentation | All Teams, PMO | 2025-07-01 | 2025-07-15 | To Do
Total Duration: |  |  |  | 2025-01-15 to 2025-07-15