## Worksheet
Growth Planning - Project Template (Startup)
Phase | Key Objective | Target Outcome | Owner | Status | Start Date | End Date (Target)
1. Discovery & Research | Identify target market, validate growth hypotheses, and gather insights. | Customer personas, pain points analysis, validated problem-solution fit. | Product Manager | In Progress | 2025-04-01 | 2025-04-15
2. MVP Development | Build a minimal viable product to test core growth mechanisms. | MVP prototype with core features, feedback loop established. | Lead Developer | Pending | 2025-04-16 | 2025-05-14
3. Early User Testing | Gather real-world usage data and iterate on product based on feedback. | Minimum 50 active users, validated feature engagement metrics. | UX Researcher | Pending | 2025-05-15 | 2025-06-14
4. Growth Loop Implementation | Integrate viral, referral, and retention mechanics into the product. | Growth loop activated; user acquisition rate increases by 25%. | Growth Hacker | Pending | 2025-06-15 | 2025-07-14
5. Scaling & Optimization | Scale successful channels and optimize conversion funnels. | Doubling of user base in 90 days, improved CAC/LTV ratio. | Marketing Lead | Pending | 2025-07-15 | 2025-10-14