## Worksheet
Growth Planning Project Template - Team Use
Phase | Objective | Key Activities | Owner(s) | Timeline (Start - End) | Status
Discovery & Research | Define market opportunities and customer needs. | - Conduct market analysis - Gather customer feedback - Review competitive landscape | Product Manager, Market Analyst | Jan 5 – Jan 20, 2024 | In Progress
Strategy Development | Create a scalable growth strategy. | - Draft growth hypothesis - Define KPIs - Prioritize initiatives | Head of Growth, Strategy Lead | Jan 21 – Feb 5, 2024 | Pending
Execution Planning | Break strategy into actionable tasks. | - Create task list - Assign responsibilities - Set milestones | Project Manager, Team Leads | Feb 6 – Feb 20, 2024 | Pending
Implementation & Testing | Launch and validate growth initiatives. | - Run A/B tests - Deploy features - Monitor early results | Engineering, Marketing, QA | Feb 21 – Apr 5, 2024 | Pending
Evaluation & Optimization | Analyze results and refine approach. | - Review KPIs - Identify bottlenecks - Iterate on strategy | Analytics Team, Product Owner | Apr 6 – Apr 30, 2024 | Pending
Total Project Duration: |  |  |  |  | Jan 5 – Apr 30, 2024
This template is designed for team collaboration and ongoing tracking of growth planning initiatives. Update statuses regularly to ensure alignment across teams.