## Worksheet
Growth Planning - Advanced Project Timeline
Phase/Activity | Start Date | End Date | Duration (Days) | Status | Owner | Budget (USD)
Phase 1: Strategy Development
Market Research & Analysis | 2023-09-05 | 2023-10-15 | 41 | Completed | Jane Smith, Strategy Lead | $8,500
Competitor Benchmarking | 2023-10-16 | 2023-11-05 | 21 | Active | Mark Johnson, Analyst | $4,800
Target Audience Definition | 2023-11-06 | 2023-11-25 | 20 | Delayed | Sarah Lee, Marketing Director | $6,000
Phase 2: Product Roadmap & Development
Product Vision & KPIs | 2023-11-26 | 2023-12-15 | 20 | Delayed | Jane Smith, Strategy Lead | $9,000
Phase 3: Marketing & Launch Campaigns
Pre-Launch Campaign Setup | 2024-01-05 | 2024-01-31 | 27 | Active | Sarah Lee, Marketing Director | $18,500
Phase 4: Post-Launch Review & Optimization
Performance Analytics & Reporting | 2024-03-01 | 2024-03-31 | 31 | Completed | Mark Johnson, Analyst | $5,200
Total Project Duration | 2023-09-05 to 2024-03-31 |  | 210 | $76,800 Total Budget