## Worksheet
Phase | Key Milestone | Start Date | End Date | Status | Responsible Team | Budget (USD)
Phase 1 | Discovery & Research | 2024-01-05 | 2024-01-31 | In Progress | Market Insights Team | $75,000
Phase 2 | Strategy Development | 2024-02-01 | 2024-03-15 | Pending | Business Strategy Group | $95,000
Phase 3 | Product Innovation & Prototyping | 2024-03-16 | 2024-05-31 | Pending | R&D Team$180,000
Phase 4 | Pilot Launch & Feedback Collection | 2024-06-01 | 2024-07-31
Phase 5 | Scale & Optimization | 2024-08-01
Total Project Budget (Estimate) | [5 empty] | $865,000