## Worksheet
Growth Planning - Project Timeline (Business Use)
Phase | Task | Start Date | End Date | Owner | Status
Market Analysis & Research | Competitor Benchmarking | 2024-01-05 | 2024-01-19 | Jane Doe | In Progress
| Target Audience Segmentation | 2024-01-22 | 2024-02-05 | John Smith | Pending
Product Development | Prototype Design Phase 1 | 2024-02-10 | 2024-03-15 | Alex Johnson | Pending
| Prototype Testing & Feedback Loop | 2024-03-18 | 2024-04-15 | Sarah Lee | Pending
| Final Product Iteration | 2024-04-18 | 2024-05-10 | Alex Johnson | Pending
Go-To-Market Strategy | Marketing Channel Planning | 2024-05-13 | 2024-06-15 | Maria Garcia | Pending
| Pricing & Packaging Strategy | 2024-06-18 | 2024-07-15 | Daniel Kim | Pending
Launch & Scaling Phase | Soft Launch (Pilot Market) | 2024-07-18 | 2024-08-31 | Jane Doe | Pending
| Full Market Rollout | 2024-09-05 | 2024-11-30 | Alex Johnson | Pending
| Performance Monitoring & Optimization | 2024-12-01 | 2025-03-31 | Maria Garcia | Pending