## Worksheet
Growth Planning - Project Timeline (Client View)
Project Duration: January 2024 – December 2024 ¦ Status: In Progress
Phase | Key Deliverables | Start Date | End Date | Status | Budget (USD)
Market Research & Analysis | Competitor analysis, customer segmentation, market sizing report | Jan 01, 2024 | Feb 28, 2024 | Completed | $15,000
Product Strategy Development | Feature roadmap, pricing model, go-to-market framework | Mar 01, 2024 | Apr 15, 2024 | Completed | $30,000
Marketing Campaign Planning | Launch strategy, digital media plan, content calendar | Apr 16, 2024 | Jun 30, 2024 | In Progress | $55,000
Product Development (Phase 1) | Core feature build, internal QA testing | May 01, 2024 | Jul 31, 2024 | In Progress | $180,000
User Acquisition & Launch | Public beta release, campaign execution, performance tracking | Aug 01, 2024 | Sep 30, 2024 | Delayed | $95,000
Customer Onboarding & Feedback Loop | Onboarding workflows, feedback collection system, support training | Oct 01, 2024 | Nov 30, 2024 | In Progress | $45,000
Growth Optimization & Scaling | Retention analysis, A/B testing framework, scaling roadmap | Dec 01, 2024 | Dec 31, 2024 | In Progress | $75,000