## Worksheet
Phase | Task | Start Date | End Date | Responsible | Status
1 | Market Research & Analysis | 2024-01-05 | 2024-01-19 | Marketing Team | In Progress
2 | Product Development Planning | 2024-01-20 | 2024-02-15 | Product Team | Not Started
3 | Prototype Development | 2024-02-16 | 2024-03-31 | Engineering Team | Not Started
4 | User Testing & Feedback | 2024-04-01 | 2024-04-30 | QA Team | Not Started
5 | Final Development & QA | 2024-05-01 | 2024-06-15 | Development Team | Not Started
6 | Go-to-Market Launch | 2024-06-16 | 2024-07-31 | Marketing & Sales Team | Not Started