## Worksheet
Growth Planning - Project Timeline Dashboard
Project Timeline ¦ Q3 2024 – Q2 2025
Phase | Activity | Start Date | End Date | Status | Progress
Planning & Research
Phase 1 | Market Analysis & Competitor Review | 2024-07-01 | 2024-08-15 | In Progress
Phase 1 | Customer Persona Development | 2024-08-16 | 2024-09-30 | Pending
Product Development
Phase 2 | Feature Design & Wireframing | 2024-10-01 | 2024-11-30 | Pending
Phase 2 | Prototype Development | 2024-12-01 | 2025-01-31 | Pending
Testing & Launch
Phase 3 | User Acceptance Testing (UAT) | 2025-02-01 | 2025-03-15 | Pending
Phase 3 | Soft Launch & Feedback Collection | 2025-03-16 | 2025-04-30 | Pending
Growth & Scaling
Phase 4 | Full Market Rollout | 2025-05-01 | 2025-06-30 | Pending
Phase 4 | Performance Optimization & KPI Review | 2025-07-01 | 2025-08-31 | Pending