## Worksheet
Growth Planning - Project Timeline (Detailed)
Phase | Task Name | Start Date | End Date | Status | Responsible Team/Person | Description
Phase 1: Discovery & Research | Market Analysis and Competitor Review | 2024-01-05 | 2024-01-19 | In Progress | Marketing Team | Analyze target market trends and competitor strategies.
| User Persona Development | 2024-01-20 | 2024-01-31 | Pending | Product Design Team | Create detailed customer personas based on research.
| Milestone: Research Completion | Research Phase Complete
Phase 2: Strategy Development | Define Growth Goals and KPIs | 2024-02-01 | 2024-02-15 | Pending | C-Level & Strategy Team | Establish measurable objectives for the next 18 months.
| Channel Strategy Formulation | 2024-02-16 | 2024-03-01 | Pending | Marketing & Sales Teams | Determine optimal growth channels and investment focus.
| Milestone: Strategy Approval | Strategy Approved
Phase 3: Execution & Implementation | Launch MVP (Minimum Viable Product) | 2024-03-05 | 2024-04-15 | Pending | Product & Engineering Teams | Develop and deploy initial product version for user testing.
| Campaign Launch: Digital Marketing | 2024-04-16 | 2024-05-31 | Pending | Marketing Team | Execute targeted digital advertising across platforms.
| User Feedback Collection & Iteration | 2024-06-01 | 2024-07-31 | Pending | Product & UX Teams | Gather feedback and implement product improvements.
| Milestone: First Growth Cycle Complete | First Growth Cycle Achieved
Phase 4: Scaling & Optimization | Expand to New Markets (Region A) | 2024-08-01 | 2024-10-31 | Pending | International Growth Team | Leverage insights to expand operations into Region A.
| Performance Optimization & Automation | 2024-11-01 | 2025-01-31 | Pending | Engineering & Ops Teams | Improve system efficiency and automate routine processes.
| Milestone: Full Scale Deployment Achieved | Scale Phase Complete
Total Duration:18 months (Jan 2024 – Jun 2025) ¦Status:Project in Progress ¦Next Review Date:July 1, 2025