## Worksheet
Project | Phase | Start Date | End Date | Status | Responsible Employee
Growth Initiative X1 | Planning & Research | 2024-01-15 | 2024-03-31 | In Progress | Jane Smith
Growth Initiative X1 | Development & Testing | 2024-04-01 | 2024-06-30 | Not Started | Mark Johnson
Growth Initiative X1 | Deployment & Launch | 2024-07-01 | 2024-08-15 | Not Started | Lisa Brown
Growth Initiative X2 | Market Analysis | 2024-02-01 | 2024-03-31 | In Progress | David Lee
Growth Initiative X2 | Strategy Development | 2024-04-01 | 2024-05-31 | Not Started | Amanda Wilson
Growth Initiative X3 | Product Design & Prototyping | 2024-01-20 | 2024-05-15 | In Progress | Ryan Taylor
Growth Initiative X3 | User Testing & Feedback | 2024-05-16 | 2024-07-31 | Not Started | Sophia Martinez
Growth Initiative X3 | Final Implementation | 2024-08-01 | 2024-09-30 | Not Started | James White