## Worksheet
Growth Planning - Project Timeline (Extended)
Phase | Task Name | Start Date | End Date | Status | Owner(s) | Budget (USD)
Planning & Strategy | Define Growth Objectives | 2025-01-05 | 2025-01-14 | Active | Jane Doe, Michael Lee | $8,500
Research & Analysis | Market Research and Segmentation | 2025-01-15 | 2025-01-31 | Pending | Lisa Park, Carlos Mendez | $12,750
Strategy Development | Create Go-to-Market Plan | 2025-02-01 | 2025-02-14 | Active | Jane Doe, Sarah Chen | $9,800
Product Alignment | Align Product Roadmap with Growth Goals | 2025-02-15 | 2025-03-14 | Pending | Robert Kim, Elena Torres | $7,600
Marketing & Outreach | Landing Page and Campaign Launch (Phase 1) | 2025-03-15 | 2025-04-30 | Pending | Maria Lopez, James Ward | $38,400
Customer Acquisition | Scaling Paid Channels (Paid Ads & Social) | 2025-05-01 | 2025-06-30 | Pending | Alex Turner, Olivia Bennett | $75,900
Retention & Engagement | Develop Onboarding and Retention Programs | 2025-07-01 | 2025-08-31 | Pending | Nina Patel, David Kim | $46,300
Performance Review & Optimization | Quarterly Growth Review and Iteration | 2025-09-01 | 2025-10-31 | Pending | Jane Doe, Michael Lee, Sarah Chen | $24,600
Total | Project Summary: |  |  |  |  | $317,850
Legend:Active¦Pending¦Completed
Note: This timeline is subject to change based on quarterly review cycles and feedback. All dates are estimated.