## Worksheet
Growth Planning - Project Timeline
Freelancer Style ¦ Track milestones, tasks, and key deliverables for maximum growth alignment.
Phase | Task | Start Date | End Date | Status | Owner | Budget (USD)
Phase 1 Discovery & Research | Market Analysis and Competitor Benchmarking | 2025-04-01 | 2025-04-15 | Pending | Alice Chen | $850
| Target Audience Persona Development | 2025-04-16 | 2025-04-30 | Pending | Alice Chen | $750
Phase 2 Strategy & Planning | Define Growth Objectives and KPIs | 2025-05-01 | 2025-05-14 | Pending | James Reed | $900
| Content and Messaging Strategy Framework | 2025-05-15 | 2025-06-01 | Pending | Sophia Liu | $800
Phase 3 Execution & Launch | Website Redesign and Optimization (V1) | 2025-06-02 | 2025-07-15 | Pending | Marcus Torres | $3,400
| Launch Email Campaign (Phase 1) | 2025-07-16 | 2025-08-31 | Pending | Laura Kim | $1,600
Phase 4 Monitoring & Iteration | Monthly Performance Review and Adjustment | 2025-09-01 | 2025-12-31 | Pending | All Team Members | $6,500
*Note: All dates are tentative and subject to client feedback. Status updates will be reviewed bi-weekly.