## Worksheet
Growth Planning - Project Timeline
Phase / Milestone | Start Date | End Date | Status | Owner(s) | Dependencies
Phase 1: Research & Discovery
Market Analysis | 2024-04-01 | 2024-05-15 | In Progress | Jane Smith, Alex Lee | N/A
Customer Persona Development | 2024-05-16 | 2024-06-30 | In Progress | Sarah Johnson, Mark Turner | Market Analysis Complete
Phase 2: Strategy & Planning
Business Model Design | 2024-07-01 | 2024-08-15 | In Progress | Daniel Reed, Emily Chen | Customer Persona Development Complete
Growth Strategy Framework | 2024-08-16 | 2024-09-30 | Delayed | Jane Smith, Sarah Johnson | Business Model Design Complete
Phase 3: Implementation & Launch
Product Development Sprint 1 | 2024-10-01 | 2024-11-30 | Completed | Mark Turner, Emily Chen, Alex Lee | Growth Strategy Framework Approved
User Testing & Feedback Integration | 2024-12-01 | 2025-01-31 | N/A | Sarah Johnson, Daniel Reed | Product Development Sprint 1 Complete
Phase 4: Post-Launch Growth & Optimization
Go-to-Market Campaign Launch | 2025-02-01 | 2025-03-31 | N/A | Jane Smith, Mark Turner, Alex Lee | User Testing Complete & Feedback Integrated
Performance Analytics Dashboard Setup | 2025-04-01 | 2025-04-30 | Completed | Emily Chen, Daniel Reed | N/A
Legend: