## Worksheet
Growth Planning - Project Timeline (Manager View)
Project Duration: January 2024 – December 2024 ¦ Status Update: April 5, 2024
Phase | Key Milestone | Start Date | Target End Date | Status | Owner (Team) | Budget Allocated ($)
Discovery & Research | Market Needs Assessment | Jan 1, 2024 | Feb 15, 2024 | Completed | Data Insights Team | 45,000
| Competitor Analysis Report | Feb 16, 2024 | Mar 31, 2024 | Completed | Market Intelligence Unit | 35,000
| Customer Persona Development | Apr 1, 2024 | Apr 30, 2024 | In Progress | User Research Team | 55,000
Strategy & Planning | Growth Strategy Framework Draft | May 1, 2024 | Jun 15, 2024 | Pending Start | Strategy Division | 65,000
| Resource Allocation Plan Review | Jun 16, 2024 | Jul 31, 2024 | Pending Start | Finance & Ops Team | 50,000
| Final Growth Plan Approval (Stakeholder) | Aug 1, 2024 | Aug 31, 2024 | Pending Start | Executive Leadership | 30,000
Execution Phase I (Q3) | Product Enhancement Sprint 1 | Sep 1, 2024 | Oct 15, 2024 | Pending Start | Product Development Team | 85,000
| User Onboarding Campaign Launch | Sep 1, 2024 | Oct 31, 2024 | Pending Start | Marketing & Sales Team | 75,000
| KPI Dashboard Implementation (Phase 1) | Oct 1, 2024 | Oct 31, 2024 | Pending Start | Analytics & IT Team | 40,000
| Total Project Budget (Estimated) | [5 empty] | 575,000
Note:All dates are subject to change based on stakeholder feedback and market dynamics. Status updates will be reviewed bi-weekly.