## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Status | Target Completion Date
January | Inception & Planning | Define objectives, scope, stakeholders, and resource needs. | Project Management Office | Completed | 2024-01-31
February | Market Research & Analysis | Analyze market trends, customer needs, and competitive landscape. | Marketing & Analytics | In Progress | 2024-02-29
March | Strategy Development | Create growth strategies and define KPIs. | Strategy & Leadership | Pending | 2024-03-31
April | Resource Allocation & Budgeting | Assign team members and finalize project budget. | Finance & HR | Pending | 2024-04-30
May | Prototype Development | Develop initial product/service prototypes. | R&D Team | Pending | 2024-05-31
June | User Testing & Feedback Collection | Conduct pilot tests with target users. | Product & UX Team | Pending | 2024-06-30
July | Iteration & Refinement | Incorporate feedback and improve prototypes. | R&D & Design | Pending | 2024-07-31
August | Go-to-Market Planning | Develop marketing, sales, and launch strategies. | Marketing & Sales | Pending | 2024-08-31
September | Full-Scale Launch Preparation | Finalize operations, training, and distribution plans. | Operations & Logistics | Pending | 2024-09-30
October | Limited Market Launch | Roll out product/service to select markets. | Marketing & Sales Team | Pending | 2024-10-31
November | Metric Evaluation & Optimization | Analyze performance data and adjust strategies. | Analytics & Leadership | Pending | 2024-11-30
December | Annual Review & Planning for Next Cycle | Evaluate overall success and plan for year 2. | All Teams | Pending | 2024-12-31