## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Status | Description
Initiation & Planning | 2023-10-01 | 2023-10-15 | Strategy Team | In Progress | Craft project scope, objectives, and resources.
Market Research & Analysis | 2023-10-16 | 2023-11-05 | Market Insights Team | Pending | Gather industry data, customer insights, and competitive analysis.
Product Development (Phase 1) | 2023-11-06 | 2024-01-15 | R&D Team | Pending | Create initial product prototype and validate core features.
User Testing & Feedback | 2024-01-16 | 2024-02-15 | Product UX Team | Pending | Collect feedback from pilot users and refine design.
Production Scaling | 2024-02-16 | 2024-04-30 | Operations & Supply Chain | Pending | Scale manufacturing and logistics to meet projected demand.
Go-to-Market Launch | 2024-05-01 | 2024-05-31 | Marketing & Sales Team | Pending | Execute full launch campaign and customer acquisition.
Performance Review & Optimization | 2024-06-01 | 2024-07-31 | All Teams | Pending | Analyze KPIs, optimize processes, and plan next phase.
Total Duration: |  |  |  |  | 26 weeks