## Worksheet
Growth Planning - Project Timeline
Phase / Milestone | Start Date | End Date | Status | Responsible Team | Key Deliverables
Market Research & Analysis | 2024-01-15 | 2024-02-15 | In Progress | Research & Insights | Competitor analysis, customer personas, market trends report
Strategy Development | 2024-02-16 | 2024-03-15 | Pending | Product Management | Growth strategy document, KPIs, success metrics framework
Resource Allocation & Budgeting | 2024-03-16 | 2024-03-31 | Pending | Finance & Operations | Budget plan, team assignments, tooling requirements
Initial Campaign Launch (Pilot) | 2024-04-01 | 2024-05-15 | Pending | Marketing & Sales | Pilot campaign execution, performance data collection
Data Review & Optimization Phase 1 | 2024-05-16 | 2024-06-15 | Pending | Analytics & Product Team | A/B test results, campaign optimization recommendations
Full-Scale Rollout Planning | 2024-06-16 | 2024-07-15 | Pending | Project Management Office | Roadmap finalization, cross-functional alignment plan
Full-Scale Campaign Launch | 2024-07-16 | 2024-09-30 | Pending | Marketing & Sales Teams | Campaign execution across all channels, real-time monitoring
Mid-Cycle Performance Review | 2024-09-15 | 2024-10-31 | Pending | Executive Leadership & Analytics | Performance assessment, pivot decisions, resource reallocation
Scaling Initiatives Implementation | 2024-11-01 | 2025-01-31 | Pending | All Teams (Cross-functional) | Scaling processes, automation upgrades, team expansion plans
Final Review & Q4 Planning | 2025-02-01 | 2025-03-15 | Pending | Executive Team & Strategy Office | Annual performance summary, next year's growth roadmap
This project timeline is designed for one-page viewing and planning. Status updates should be reviewed monthly.