## Worksheet
Phase / Milestone | Start Date | End Date | Duration (Days) | Status | Responsible Team
Initiation & Planning | 2024-01-15 | 2024-01-31 | 17 | Planned | Growth Strategy Team
Market Research & Analysis | 2024-02-01 | 2024-03-15 | 43 | Planned | Market Insights Team
User Persona Development | 2024-03-16 | 2024-04-15 | 31 | Planned | User Experience Team
Growth Strategy Design | 2024-04-16 | 2024-05-31 | 46 | Planned | Growth Strategy Team
Prototype & Testing Phase 1 | 2024-06-01 | 2024-07-15 | 45 | Planned | R&D Team
Feedback Integration & Refinement | 2024-07-16 | 2024-08-31 | 47 | Planned | Product Team
Pilot Launch (Limited Scale) | 2024-09-01 | 2024-10-31 | 61 | Planned | Marketing & Operations Team
Evaluation & Optimization | 2024-11-01 | 2024-11-30 | 30 | Planned | Data Analytics Team
Full-Scale Rollout | 2024-12-01 | 2025-03-31 | 121 | Planned | All Departments