## Worksheet
Growth Planning - Project Timeline
Phase | Task Name | Start Date | End Date | Status | Responsible Team/Person
Planning & Discovery | Market Research & Analysis | 2024-01-05 | 2024-01-19 | In Progress | Alex Johnson (Marketing)
| Target Audience Definition | 2024-01-20 | 2024-01-31 | Pending | Sarah Lee (Product)
| Growth Strategy Development | 2024-02-01 | 2024-02-15 | Pending | James Carter (Strategy)
Development & Implementation
| Product Feature Development | 2024-02-16 | 2024-04-15 | In Progress | Lisa Wong (Engineering)
| UX/UI Design & Testing | 2024-03-15 | 2024-04-30 | Pending | Maria Rodriguez (Design)
Launch & Growth Phase
| Alpha Release & Internal Testing | 2024-05-01 | 2024-05-15 | Pending | Team A (QA)
| Public Beta Launch & Feedback Collection | 2024-05-16 | 2024-07-31 | Pending | Daniel Kim (Product)
Evaluation & Optimization
| Performance Metrics Analysis | 2024-08-01 | 2024-08-15 | Pending | Amanda Taylor (Analytics)
| Growth Strategy Refinement & Next Steps Planning | 2024-08-16 | 2024-08-31 | Pending | Jamal White (Strategy)
Total Duration: |  | 2024-01-05 to 2024-08-31