## Worksheet
Growth Planning - Project Timeline
Task ID | Activity | Owner | Start Date | End Date | Status | Budget (USD)
#GP-001 | Market Research & Analysis | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | $15,000
#GP-002 | Define Growth Strategy Framework | John Smith | 2024-04-16 | 2024-05-15 | Pending | $10,000
#GP-003 | Customer Persona Development | Sarah Lee | 2024-05-16 | 2024-06-15 | Pending | $8,000
#GP-004 | Product Roadmap Planning | Mike Johnson | 2024-06-16 | 2024-07-31 | Pending | $25,000
#GP-005 | Marketing Campaign Launch Preparation | Lisa Chen | 2024-08-01 | 2024-08-31 | Pending | $35,000
#GP-006 | Quarterly Growth Review & Reporting | Emma Wilson | 2024-11-30 | 2024-12-31 | Pending | $5,000