## Worksheet
Growth Planning - Project Timeline Report
Project Timeline Template ¦ Purpose: Growth Planning ¦ Version: Report Version
Phase / Milestone | Start Date | End Date | Status | Owner | Description / Key Activities
Initiation & Planning | 2024-01-01 | 2024-01-15 | On Hold | Jane Doe | Define objectives, stakeholders, budget allocation.
Market Research & Analysis | 2024-01-16 | 2024-02-15 | In Progress | Mike Chen | Gather customer insights, competitor benchmarking.
Strategy Development | 2024-02-16 | 2024-03-15 | In Progress | Sarah Lin | <Create growth roadmap, KPIs, and go-to-market plan.
Product/Service Design | 2024-03-16 | 2024-05-15 | Not Started | Daniel Kim | Design prototypes, user testing sessions.
Development & Testing | 2024-05-16 | 2024-07-31 | Not Started | Laura Smith | Build and QA testing of core features.
Pilot Launch (Phase 1) | 2024-08-01 | 2024-09-30 | Not Started | James Wilson | Deploy to select market segment; collect feedback.
Evaluation & Refinement | 2024-10-01 | 2024-10-31 | Not Started | Sophia Brown | Analyze pilot data; adjust strategy and timeline.
Full-Scale Rollout | 2024-11-01 | 2025-03-31 | Not Started | Ryan Taylor | Launch across all target markets; marketing campaign.
Performance Review & Optimization | 2025-04-01 | 2025-06-30 | Not Started | Elena Rodriguez | Evaluate KPIs; optimize operations and marketing.
Total Duration | 2024-01-01 to 2025-06-30 (18 months)