## Worksheet
Growth Planning - Project Timeline
Phase | Task | Start Date | End Date | Status
Research & Analysis | Market Research and Competitor Analysis | 2023-10-01 | 2023-10-15 | In Progress
Strategy Development | Define Growth Objectives and KPIs | 2023-10-16 | 2023-10-31 | Pending
Planning & Design | Create Product Roadmap and Marketing Plan | 2023-11-01 | 2023-11-15 | Pending
Execution Phase 1 | Prototype Development and Testing | 2023-11-16 | 2023-12-07 | Pending
Execution Phase 2 | User Testing and Feedback Integration | 2023-12-08 | 2023-12-15 | Pending
Launch Preparation | Finalize Launch Plan and Marketing Campaigns | 2023-12-16 | 2023-12-31 | Pending
Go-Live & Review | Product Launch and Post-Launch Evaluation | 2024-01-01 | 2024-01-31 | Pending