## Worksheet
Growth Planning - Project Timeline (Small Business)
Phase | Task | Start Date | End Date | Responsible Team | Status
Phase 1: Research & Analysis | Market Opportunity Assessment | 2024-04-01 | 2024-04-15 | Marketing Team | In Progress
| Competitor Benchmarking | 2024-04-16 | 2024-05-01 | Product Research Team | Pending
| Customer Persona Development | 2024-05-02 | 2024-05-15 | Marketing & UX Team | Pending
Phase 2: Strategy Development | Revenue Model Design | 2024-05-16 | 2024-06-15 | Finance & Strategy Team | Pending
| Growth Marketing Plan Draft | 2024-06-16 | 2024-07-15 | Marketing Team | Pending
| Resource Allocation & Budgeting | 2024-07-16 | 2024-07-31 | Finance Team | Pending
Phase 3: Execution & Launch | Product Development Sprint | 2024-08-01 | 2024-09-15 | Engineering Team | Pending
| Test Marketing Campaign (Pilot) | 2024-09-16 | 2024-10-15 | Marketing Team | Pending
| Limited Launch (Beta Version) | 2024-10-16 | 2024-11-30 | Product & Ops Team | Pending
| Full Product Launch | 2024-12-01 | 2024-12-31 | Entire Team | Pending
Phase 4: Review & Optimization | Post-Launch Performance Review | 2025-01-01 | 2025-01-31 | Strategy & Analytics Team | Pending
| Ongoing Optimization Plan | 2025-02-01 | 2025-12-31 | Product & Marketing Team | Pending
Growth Planning Project Timeline - Small Business Template ¦ Updated as of April 5, 2024