## Worksheet
Growth Planning - Project Timeline (Startup)
Phase | Task | Start Date | End Date | Status | Owner
Phase 1: Ideation & Validation
Market Research | Identify target audience and pain points | 2024-11-05 | 2024-11-15 | In Progress | Jane Doe
Concept Validation | Develop initial product concept and test with users | 2024-11-16 | 2024-11-30 | Pending | John Smith
Phase 2: Product Development
UI/UX Design | Create wireframes and prototype interface | 2024-12-01 | 2024-12-15 | Pending | Alice Brown
Core Features Build | Develop MVP with key functionalities | 2024-12-16 | 2025-01-31 | Pending | Mike Johnson
Phase 3: Launch & Growth
Pre-Launch Marketing | Build buzz through social media and email campaigns | 2025-02-01 | 2025-03-15 | Pending | Sarah Lee
Soft Launch (Beta) | Release to limited audience for feedback | 2025-03-16 | 2025-04-30 | Pending | All Team Members
Phase 4: Scale & Optimize
Full Product Launch | Official public release with marketing push | 2025-05-01 | 2025-06-30 | Pending | Jane Doe & Team
Performance Optimization | Improve speed, reliability, and user experience post-launch | 2025-07-01 | 2025-08-31 | Pending | Mike Johnson & Dev Team
Milestone |  | 2024-11-15 | 2024-11-30 | Concept Validation Complete
Milestone |  | 2024-12-15 | 2024-12-31 | UI/UX Finalized & MVP Ready for Testing
Milestone |  | 2025-04-30 | 2025-04-31 | Beta Version Successfully Tested & Feedback Integrated
Milestone |  | 2025-06-30 | 2025-06-31 | Full Launch Achieved with 1,000+ Active Users
Note: This timeline is subject to change based on feedback and resource availability. Status updates are reviewed weekly.