## Worksheet
Growth Planning - Project Timeline (Summary View)
Phase | Key Milestone | Start Date | End Date | Status | Responsible Team/Person
Market Research & Analysis | Complete Customer Needs Assessment | 2024-01-15 | 2024-03-31 | In Progress | Growth Team - Sarah Lin
Product Development | Finalize MVP Design & Prototypes | 2024-04-01 | 2024-06-30 | Pending | Product Engineering - James Wong
Go-to-Market Strategy | Launch Beta Testing Program | 2024-07-01 | 2024-09-30 | Pending | Marketing & Sales - Lisa Chen
Scaling & Expansion | Rollout to 5 New Markets | 2024-10-01 | 2025-03-31 | Pending | Global Operations - Mark Thompson
Performance Review & Optimization | Review Q1–Q4 2025 Growth Metrics | 2025-04-01 | 2025-06-30 | Pending | Data Analytics - Priya Patel
*All dates are estimated. Status and timelines subject to change based on project progress and stakeholder feedback.