## Worksheet
Growth Planning - Project Timeline (Tracking View)
Phase | Task Name | Owner | Start Date | End Date | Status | Milestone? | Action Items
Discovery | Market Research & Analysis | Jane Doe | 2024-01-05 | 2024-01-19 | In Progress | Yes | EditUpdate
Planning | Define Growth Strategy Framework | John Smith | 2024-01-20 | 2024-01-31 | In Progress | No | EditUpdate
Execution | Launch Digital Marketing Campaign | Lisa Chen | 2024-02-01 | 2024-03-15 | In Progress | Yes | EditUpdate
Execution | Product Feature Rollout (v1.0) | Mike Johnson | 2024-02-15 | 2024-03-31 | Complete | No | EditUpdate
Review & Optimize | Analyze Campaign Performance Metrics | Sarah Wilson | 2024-04-01 | 2024-04-15 | Delayed | No | EditUpdate
This tracking view is for Growth Planning purposes. Status updates should be refreshed weekly.