## Worksheet
Growth Planning - Weekly Project Timeline
Week Number | Start Date | End Date | Objective / Goal | Milestones | Status (Progress %)
Week 1 | 2024-04-01 | 2024-04-07 | Define project scope and key stakeholders | Stakeholder mapping complete, scope document approved | 95%
Week 2 | 2024-04-08 | 2024-04-14 | Conduct market analysis and competitive review | Data collection finalized, analysis report drafted | 75%
Week 3 | 2024-04-15 | 2024-04-21 | Develop initial growth strategy framework | Strategy outline approved by leadership team | 88%
Week 4 | 2024-04-22 | 2024-04-28 | Design pilot program and KPIs | Pilot plan approved; KPI dashboard prototype ready | 65%
Week 5 | 2024-04-29 | 2024-05-05 | Initiate pilot launch and gather feedback | Pilot launched; initial user feedback collected | 100%
Week 6 | 2024-05-06 | 2024-05-12 | Evaluate pilot results and refine strategy | Pilot evaluation completed; adjustments documented | 90%
Week 7 | 2024-05-13 | 2024-05-19 | Scale strategy to broader team/region | Scaled rollout plan initiated, training modules prepared | 70%
Week 8 | 2024-05-20 | 2024-05-26 | Maintain momentum and monitor key metrics | Daily tracking in place, weekly performance reports issued | 100%
Week 9 | 2024-05-27 | 2024-06-02 | Review first quarter outcomes and plan next phase | Quarterly review scheduled, strategic goals for Q3 set | 85%
Week 10 | 2024-06-03 | 2024-06-09 | Finalize growth roadmap and secure budget approval | Roadmap approved; funding request submitted to finance | 95%
Week 11 | 2024-06-10 | 2024-06-16 | Celebrate milestones and recognize team efforts | Milestone celebration event held; appreciation notes sent | 100%
Week 12 | 2024-06-17 | 2024-06-23 | Begin planning for next growth cycle (Q3) | Preliminary Q3 objectives drafted and reviewed | 80%
Growth Planning - Weekly Project Timeline ¦ Updated as of June 23, 2024