## Worksheet
Growth Planning - Project Tracker (Extended)
Project ID | Project Name | Objective | Start Date | Target End Date | Status | Progress (%)(Actual / Target) | Budget (USD) | Budget Usage (%) | Owner | Dependencies
GR-001 | New Market Expansion - APAC | Enter three new Asian markets by Q4 2024 with 5% market share target. | Jan 05, 2024 | Dec 31, 2024 | On Hold(Regulatory approval pending) | 38%(19/50) | $750,000 | 42% | Alice Chen | Legal review, Partner agreements
GR-002 | Digital Product Launch - AI Dashboard | Launch AI-powered analytics dashboard to increase user engagement by 40% in first 6 months. | Feb 15, 2024 | Jul 31, 2024 | In Progress(Testing phase) | 67%(33.5/50) | $950,000 | 61% | Robert Kim | Backend API integration, UX review
GR-003 | Cross-Platform Mobile App Redesign | Improve app retention rate by redesigning core user flows and UX. | Jan 22, 2024 | May 31, 2024 | Completed(Deployed Feb '24) | 100%(5/5) | $380,000 | 97% | Lisa Wong | Data migration, QA testing
GR-004 | Sustainability Initiative - Carbon Neutral Certification | Achieve carbon neutrality for all operations by end of 2025. | Mar 10, 2024 | Dec 31, 2025 | In Progress(Phase I complete) | 45%(9/20) | $1.2M | 38% | James Reed | Emission audit, Green partner onboarding
GR-005 | Customer Onboarding Optimization | Reduce average onboarding time from 3 days to under 12 hours. | Apr 01, 2024 | Oct 31, 2024 | At Risk(Tool integration delayed) | 33%(5/15) | $260,000 | 29% | Maya Patel | CMS update, Support team training
GR-006 | Educational Webinar Series - Q2 2024 | Host six industry webinars to strengthen brand thought leadership. | Apr 15, 2024 | Jun 30, 2024 | In Progress(3 of 6 completed) | 50%(3/6) | $75,000 | 41% | Tyler Moore | Speaker coordination, Promotion plan
GR-007 | Cloud Infrastructure Migration - Phase 2 | Migrate remaining services to secure cloud environment. | May 01, 2024 | Aug 31, 2024 | In Progress(Testing underway) | 75%(3/4) | $600,000 | 68% | Sarah Johnson | Security audit, Backup validation
GR-012 | User Feedback Integration Platform (Beta) | Build platform to collect and analyze real-time customer feedback. | Mar 20, 2024 | Ongoing(No fixed end) | In Progress(Beta release in progress) | 78%(15/19) | $420,000 | 63% | Daniel Cruz | API access setup, Privacy compliance
GR-015 | Talent Acquisition Program - Engineering Team Expansion | Hire 12 new engineers across 3 regions by Q3. | Jan 10, 2024 | Sept 30, 2024 | On Hold(Hiring freeze in place) | 58%(7/12) | $1.3M | 49% | Sophia Liu | Budget approval required
GR-021 | Brand Identity Refresh - Global Rebranding Initiative | Revamp brand elements (logo, messaging, visual tone) for global consistency. | Feb 28, 2024 | Nov 30, 2024 | In Progress(Design phase complete) | 65%(13/20) | $875,000 | 62% | Jessica Bell | Licensing review, Market testing
Legend:
On Hold– Project paused due to external factors.
In Progress– Actively underway with minor delays or risks.
Completed– Milestone achieved and verified.