## Worksheet
Weekly Project Tracker - Growth Planning
Project Name | Owner | Status | Start Date | Target End Date | This Week's Goals | Last Week's Progress | Action Items / Roadblocks | Notes / Updates
Product Launch Campaign 2024 | Marketing Team | In Progress | 2024-03-18 | 2024-05-31 | Promotional content draft completed, social media calendar locked in. | Finalized 5 campaign creatives; began A/B testing. | Approval delay from legal team on compliance check. | Expected resolution by Friday. Adjusted timeline accordingly.
User Onboarding Enhancement | Product Team | On Hold | 2024-03-15 | 2024-06-15 | User feedback integration into onboarding flow. | Began usability testing with 15 users; data collected. | Server performance bottleneck identified during testing. | Dev team investigating. Delay expected next week.
Data Analytics Dashboard | Analytics Team | Planned | 2024-04-01 | 2024-05-15 | Sprint 3: Finalize KPIs and build core metrics widgets. | Sprint 2 completed; initial design approved. | Requires access to new data source API (pending IT). | API access granted Tuesday. Re-scheduling sprint goals.
Cross-Platform Sync Feature | Engineering Team | In Progress | 2024-03-10 | 2024-07-15 | Backend integration testing completed; frontend implementation in progress. | Fixed 8 bugs; performance improved by 35%. | No major roadblocks. Minor UI alignment issues reported. | Team will conduct code review on Friday to finalize milestone.
Weekly Update: April 5 - April 11, 2024