## Worksheet
Growth Planning - Schedule Planner (Client View)
Phase | Key Milestone | Start Date | End Date | Status | Budget Allocated ($)
Initiation & Discovery | Project Kickoff & Requirements Finalization | 2024-01-15 | 2024-01-31 | In Progress | 7,500.00
Strategy & Planning | Milestone 1: Growth Strategy Approved by Client | 2024-02-01 | 2024-03-15 | Pending Approval | 15,000.00
Design & Development | Milestone 2: UI/UX Prototypes Delivered & Reviewed | 2024-03-16 | 2024-05-15 | Not Started | 35,000.00
Testing & QA | Milestone 3: System Validation Complete (UAT Passed) | 2024-05-16 | 2024-06-15 | Not Started | 18,000.00
Deployment & Launch | Milestone 4: Full Platform Live & Operational | 2024-06-16 | 2024-07-31 | Not Started | 25,000.00
Ongoing Optimization | Milestone 5: First Growth Report & Recommendations Released | 2024-08-01 | 2024-12-31 | Not Started | 30,000.00
Total Project Budget: |  |  |  |  | $125,500.00
Note:This schedule is subject to change based on client feedback and resource availability. All dates are estimated.