## Worksheet
Phase | Objective | Timeline (Start - End) | Metric/KPI | Status
Initiation | Define growth goals and scope | Jan 1 - Jan 15 | Goals documented, stakeholder approval | In Progress
Research & Analysis | Gather market and customer insights | Jan 16 - Feb 5 | 2+ competitor reports, 300+ survey responses | Not Started
Strategy Development | Create growth strategy and roadmap | Feb 6 - Feb 20 | Approved strategy document, stakeholder sign-off | Not Started
Pilot Testing | Run small-scale test of key initiatives | Feb 21 - Mar 10 | 5% conversion lift, positive feedback from pilot group | Not Started
Full Implementation | Deploy selected initiatives across channels | Mar 11 - Apr 30 | All planned features live, KPI tracking enabled | Not Started
Evaluation & Optimization | Analyze results and refine strategy | May 1 - May 15 | Final report, recommendations for Q3 planning | Not Started