## Worksheet
Growth Planning Schedule Planner - Extended
Phase | Task/Activity | Start Date | End Date | Owner(s) | Status | Budget Allocation ($)
Phase 1: Strategy & Analysis (Weeks 1-4)
Q1 | Market Research & Competitor Analysis | 2023-09-01 | 2023-09-15 | Jane Doe (Marketing) | In Progress | 15,000
Milestone: Market Insights Report Submitted
Phase 2: Planning & Design (Weeks 5-8)
Q1 | Define Growth Objectives & KPIs | 2023-09-16 | 2023-09-30 | John Smith (Strategy) | Pending | 8,500
Milestone: Growth Strategy Document Approved
Phase 3: Development & Implementation (Weeks 9-16)
Q2 | Product Enhancement Roadmap | 2023-10-01 | 2023-10-31 | Alex Lee (Product) | Pending | 45,000
Q2 | Digital Marketing Campaign Launch | 2023-11-01 | 2023-11-30 | Jane Doe (Marketing) | Pending | 65,000
Phase 4: Monitoring & Optimization (Weeks 17-20)
Q3 | KPI Tracking & Monthly Performance Review | 2023-12-01 | 2024-01-31 | John Smith (Strategy) | Pending | 15,500
Phase 5: Scaling & Expansion (Weeks 21-24)
Q3 | Launch New Market Entry Strategy | 2024-01-01 | 2024-03-31 | Alex Lee (Product), Jane Doe (Marketing) | Pending | 85,000
Final Milestone: Growth Plan Completion & Executive Review
Note: This schedule is based on a 24-week timeline. Adjustments may be made based on performance data and stakeholder feedback.