## Worksheet
Week | Goal / Objective | Key Tasks | Status | Owner
Week 1 | Growth Strategy Development | - Define target audience - Analyze current market position - Set SMART goals for next quarter | Pending | Project Lead
Week 2 | Marketing Campaign Planning | - Draft content calendar - Design social media graphics - Finalize email marketing sequence | Pending | Marketing Specialist
Week 3 | Content Creation & Publishing | - Produce 2 blog posts - Shoot 1 video content - Launch first social media campaign | Pending | Content Creator
Week 4 | Performance Monitoring & Feedback Loop | - Track campaign metrics - Gather user feedback - Adjust strategy based on insights | Pending | Data Analyst
Week 5 | Partnership & Collaboration Outreach | - Identify potential partners - Draft outreach emails - Schedule initial calls | Pending | Business Development
Week 6 | Lead Generation & Conversion Optimization | - Optimize landing pages - Run A/B tests on CTAs - Launch paid ads campaign (Google & Meta) | Pending | Conversion Specialist
Week 7 | Customer Onboarding Enhancement | - Revise onboarding flow - Add welcome email sequence - Implement feedback forms | Pending | Product Manager
Week 8 | Review & Adjust Strategy for Next Phase | - Evaluate progress - Hold retrospective meeting - Set Q3 targets | Pending | Project Lead
Milestone: Quarterly Growth Launch Complete