## Worksheet
Growth Planning - Schedule Planner (Manager View)
Task ID | Project / Initiative | Owner | Start Date | End Date | Status | Budget (USD)(Allocated) | Milestones Achieved / Target% Complete | Next Actions & DependenciesKey Risks / Notes
GP-001 | New Product Launch: Q3 2024 | Sarah Thompson | 2024-06-15 | 2024-11-30 | In Progress | $85,000 | 78% / 95%(6/9) | Finalize marketing campaign Review prototype testing Risk:Supplier delay on component
GP-002 | Talent Acquisition Strategy(Enterprise Scale) | James Reed | 2024-05-10 | 2024-12-31 | In Progress | $65,000 | 67% / 94%(8/12) | Hire 5 key roles Launch internal mobility program Risk:High competition in tech talent pool
GP-003 | Digital Transformation Roadmap(Phase II) | Linda Chen | 2024-07-20 | 2025-03-15 | Delayed (Pending Review) | $145,000 | 35% / 86%(9/27) | Wait for executive approval on architecture Coordinate with IT Security Team Risk:Regulatory compliance concerns
GP-004 | Customer Retention Program(New Model) | Michael O'Connor | 2024-06-25 | 2025-01-31 | Completed (Pending Review) | $48,500(Actual) | 100% / 98%(7/7) | Present results to leadership Document lessons learned Note:Achieved 12% increase in retention
GP-005 | Merge & Acquisition Prep: Target X(Due Diligence Phase) | Emma Wilson | 2024-08-15 | 2024-11-30 | Completed (Approved) | $79,300(Actual) | 100% / 95%(5/5) | Finalize integration plan Schedule due diligence team syncs Note:Acquired with full approval