## Worksheet
Growth Planning - Schedule Planner
Week | Start Date | End Date | Objective/Key Activity | Status | Owner | Metric/KPI Target
Q1 Planning Phase - January 2024
Week 1 | Jan 1, 2024 | Jan 7, 2024 | Market Research & Competitor Analysis | In Progress | Jane Doe - Marketing Lead | Complete 5 competitor profiles; gather insights on pricing strategies.
Week 2 | Jan 8, 2024 | Jan 14, 2024 | User Persona Development | To Do | Mark Lee - Product Manager | Create 3 detailed user personas.
Q1 Execution Phase - February 2024
Week 3 | Jan 15, 2024 | Jan 21, 2024 | Product Roadmap Finalization | In Progress | Mark Lee - Product Manager | Finalize roadmap with quarterly milestones.
Week 4 | Jan 22, 2024 | Jan 28, 2024 | Launch Campaign Strategy Development | To Do | Jane Doe - Marketing Lead | Define campaign themes, channels, and budget allocation.
Q1 Review & Adjustment - March 2024
Week 5 | Jan 29, 2024 | Feb 4, 2024 | Stakeholder Alignment Meeting | In Progress | All Department Heads | Confirm alignment on goals and resource allocation.
Week 6 | Feb 5, 2024 | Feb 11, 2024 | KPI Dashboard Setup & Data Integration | To Do | Alex Chen - Data Analyst | Implement tracking for all core KPIs.