## Worksheet
Growth Planning - Schedule Planner (Startup)
Track key milestones, tasks, and timelines for your startup’s growth journey
Phase | Key Objective | Task Description | Owner | Start Date | End Date | Status
Phase 1: Ideation & Validation
Q1 | Validate core idea with target users | Conduct 25 user interviews and surveys | Jane Doe (Product) | 2025-01-01 | 2025-03-31 | In Progress
Q1 | Create initial product prototype | Develop wireframe and clickable prototype | Mike Smith (Design) | 2025-01-15 | 2025-03-31 | Pending
Phase 2: MVP Development & Testing
Q2 | Build Minimum Viable Product (MVP) | Develop core features for beta testing | Lisa Chen (Engineering) | 2025-04-01 | 2025-06-30 | Pending
Q2-Q3 | Internal QA & Beta Testing | Run 8-week beta with 100 early users | Tom Wilson (QA) | 2025-05-15 | 2025-07-31 | Pending
Phase 3: Go-To-Market & Scaling
Q3 | Landing page & pre-launch campaign | Launch website, email list, and social media funnel | Sarah Lee (Marketing) | 2025-07-01 | 2025-08-31 | Pending
Q4 | Official launch & first 1,000 users | Go live with full product and acquisition campaign | All Teams (Cross-functional) | 2025-10-15 | 2025-12-31 | Pending
Phase 4: Growth & Iteration
Q1 2026 | Scale user acquisition | Implement paid ads and referral program | Sarah Lee (Marketing) | 2026-01-01 | 2026-03-31 | Pending
Q2 2026 | Incorporate user feedback into v1.5 update | Add top 5 requested features and improve UX | Mike Smith (Design) | 2026-04-15 | 2026-06-30 | Pending