## Worksheet
Growth Planning - Schedule Planner (Summary View)
Project Phase | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status | % Complete
Phase 1: Market Research & Feasibility Analysis
Market Demand Analysis | 2024-04-05 | 2024-05-15 | 2024-04-10 | 2024-05-13 | Completed
Competitor Benchmarking | 2024-04-15 | 2024-06-30 | 2024-05-18 | - | Delayed
Phase 2: Product Development & Prototyping
Core Feature Design | 2024-06-01 | 2024-08-15 | - | - | Pending
Prototype Development | 2024-08-16 | 2024-10-31 | - | - | Pending
Phase 3: Go-to-Market Strategy & Launch
Marketing Campaign Planning | 2024-11-01 | 2025-01-31 | - | - | Pending
Customer Onboarding Program | 2025-01-15 | 2025-03-31 | - | - | Pending
Total Phases | - |  | - |  | Overall Status
Last Updated: April 5, 2024 ¦ Projected Completion Date: Q3 2025