## Worksheet
Growth Planning - Schedule Planner (Tracking View)
Project: Q4 Market Expansion Initiative
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete | Action
TASK001 | Market Research & Analysis | Marketing Team | 2023-10-01 | 2023-10-15 | Ongoing | 75% | Edit
TASK002 | Define Target Customer Segments | Sales Strategy Team | 2023-10-16 | 2023-10-31 | Ongoing | 45% | Edit
TASK003 | Develop New Product Features | R&D Department | 2023-10-15 | 2023-11-20 | Delayed | 60% | Edit
TASK004 | Design & Prototype Testing | Product Design Team | 2023-11-21 | 2023-12-15 | Completed | 100% | Edit
TASK005 | Prepare Go-To-Market Campaign | Marketing Team | 2023-12-16 | 2024-01-15 | Completed | 100% | Edit
TASK006 | Finalize Sales Training Modules | Sales Enablement Team | 2024-01-16 | 2024-01-31 | Completed | 100% | Edit
TASK007 | Launch & Monitor Market Performance | Exec Team & Operations | 2024-02-01 | 2024-03-31 | Delayed (Pending Approval) | 15% | Edit
Total Tasks:7 ¦Completed:3 ¦Ongoing:2 ¦Delayed:2