## Worksheet
Task ID | Task Name | Description | Owner | Due Date | Priority | Status(Progress) | Budget (USD)
TASK-001 | Market Research Expansion | Conduct in-depth analysis of emerging markets for Q3 expansion strategy. | Sarah Johnson | 2024-06-30 | High | In Progress (65%) | 18,500.00
TASK-002 | Product Feature Roadmap Planning | Define key features and timeline for the Q4 product release. | Michael Chen | 2024-07-15 | Medium | In Progress (45%) | 32,000.00
TASK-003 | Customer Onboarding UX Upgrade | Redesign onboarding flow to improve retention by 15%. | Linda Martinez | 2024-07-25 | High | In Progress (30%) | 16,800.00
TASK-004 | Employee Training Program Launch | Develop and roll out new training modules for sales team. | Daniel Reed | 2024-08-10 | Medium | Delayed (15%) | 9,300.00
TASK-005 | SEO & Content Strategy Update | Revamp content calendar and optimize on-page SEO for key pages. | Aisha Patel | 2024-06-28 | Low | Completed (100%) | 5,500.00
TASK-006 | CRM System Integration Project | Integrate new CRM with marketing automation platform. | James Wilson | 2024-07-31 | High | In Progress (80%) | 56,750.00
TASK-007 | Quarterly Sales Forecast Modeling | Create predictive model for Q3 sales based on historical and market data. | Emily Roberts | 2024-07-18 | Medium | In Progress (75%) | 12,900.00
TASK-008 | Brand Identity Refresh (Phase 1) | Revise logo, color palette, and brand messaging for new market launch. | Claudia Lopez | 2024-08-20 | High | In Progress (55%) | 38,400.00
TASK-009 | Internal Feedback Survey Deployment | Send out employee survey to assess workplace satisfaction and engagement. | Ryan Kim | 2024-06-31 | Low | Completed (100%) | 3,750.00
TASK-010 | Partnership Proposal Drafting | Prepare formal proposal for strategic partnership with TechNova Inc. | Nina Alvarez | 2024-07-28 | Medium | In Progress (50%) | 14,600.00
Total Project Budget: | [6 empty] | $245,100.00